## US20
Test Scenarios for SimpCity
| Test Cases Creation |  |  | System Testing (TDA) |  |  | User Acceptance Testing |  | Team
| User Stories: | US20 - As a user, I want to be able to go back to the main menu after I have ended the game. |  | Version Control: | V1 |  | Version Control: | V1 | Scrum Master: | Megan Png
| Created By: | Hui Ying |  | Tester: |  |  | User: |  | Tech Lead: | Claris
| Status: |  |  | Status: |  |  | Status:
| Dated as of: | 2021-12-15 |  | Test Date: |  |  | UAT Date: |  | QA: | Hui Ying
| Reviwed By: |  |  | Reviwed By: |  |  | Reviwed By: |  | Developer: | Amanda Chan
| Tech Lead | <Signature> |  | Scrum Master | <Signature> |  | Scrum Master: | <Signature>
| Scrum Master | <Signature> |  |  |  |  | Tech Lead: | <Signature>
[7 empty] | QA: | <Signature>
condition to test Start New Game Feautre
S/NO | Test Scenario | Test Scenario Description | Test Values | Expected Outcome | Boundary? Equivalence? | Functional? Non-Functional? | Pass/ Fail | Actual Outcome | Test Result (Pass / Fail) | Remarks
1 | The number "0" is inputted by the user | 1. The user enters an option value of the numeric interger "0" when prompted | Before: Start New Game option is selected After: Your Choice? 0 | The user return to the main menu, the main menu options is display to them | Equivalence | Functional | Pass
2 | The number ranging from "1" to "5" is inputted by the user | 1. The user enters an option value that is not a numeric interger of "0" but within the menu options when prompted | Before: Start New Game option is selected After: Your Choice? [Any input in the menu from "1" to "5" but not 0] | The options will be processed according to the menu options selected | Boundary | Functional | Pass
3 | The number"0" to "5" is not inputted by the user | 1. The user enters an option value that is not within the menu | Before: Start New Game option is selected After: Your Choice? [Anything not within the menu] | An error message shall be displayed to remind the users that invalid input is captured | Equivalence | Functional | Pass
4 | The number "0" to "5" is not inputted by the user | 1. The user enters an any value except "0" to "5". 2. The user renters the option value "0" when the "Your Choice?" is prompted. 3. The users selects the Start New Game option again 4. The users enters the value from that is in the configure menu from either "1" to "5" | Before: | Start New Game option is selected |  | Functional
|  |  | After: 1. [Any value except "0" to "5"] | 1. An error message shall be displayed to remind the users only number "0" to "5" will be accepted | Boundary |  | Fail
|  |  | After: 2. Nominal value: 0 | 2. The users shall be brought back to the main menu |  |  | Pass
|  |  | After: 3. Values from "1" to "5" | 3. The system shall process the option value inputted accordingly. The user expects to see partial output not returning an output or prompt. |  |  | Pass

## US1
Test Scenarios for SimpCity
| Test Cases Creation |  |  | System Testing (TDA) |  |  | User Acceptance Testing |  | Team
| User Stories: | US1 - As a user, I want to be able to start a new game so I may play the game. |  | Version Control: | V1 |  | Version Control: | V1 | Scrum Master: | Megan Png
| Created By: | Hui Ying |  | Tester: |  |  | User: |  | Tech Lead: | Claris
| Status: |  |  | Status: |  |  | Status: |  | QA: | Hui Ying
| Dated as of: | 2021-12-15 |  | Test Date: |  |  | UAT Date: |  | Developer: | Amanda Chan
| Reviwed By: |  |  | Reviwed By: |  |  | Reviwed By:
| Tech Lead | <Signature> |  | Scrum Master | <Signature> |  | Scrum Master: | <Signature>
| Scrum Master | <Signature> |  |  |  |  | Tech Lead: | <Signature>
[7 empty] | QA: | <Signature>
| condition to test Start New Game Feautre | steps
S/NO | Test Scenario | Test Scenario Description | Test Values | Expected Outcome | Boundary? Equivalence? | Functional? Non-Functional? | Pass/ Fail | Actual Outcome | Test Result (Pass / Fail) | Remarks
1 | The number "1" is inputted by the user. | 1. The user enters an option value of the numeric interger "1" when the message "Your Choice?" is prompted to the users | Before: Main Menu is displayed After: Your Choice? 1 | A empty 4x4 board with the message "Turn 1" shall be displayed to the users. The confiugration menu with an option rangning from "0" to "5" should be displayed to the users. | Equivalence | Functional | Pass
2 | The number "1" is inputted by the user, then option value "1" is entered again | 1. The user enters an option value of the numeric interger "1" when the message "Your Choice?" is prompted to the users, then the user enter the numeric integer "1" again to build a building | Before: Main Menu is displayed After: Your Choice? 1 Your Choice? 1 b2 | A empty 4x4 board with the message "Turn 1" shall be displayed to the users. The confiugration menu with an option rangning from "0" to "5" should be displayed to the users. A message "Build where?" is printed to prompt the user to enter a position | Equivalence | Functional | Pass
3 | The number "1" is inputted by the user. | 1. The users enters any value except "0" to "2" 2. The user re-enters an option value of the numeric interger "1" when the message "Your Choice?" is prompted to the users. 3. The user selects the option value of "0" to exit to the main menu 4. The user enters any value between "0" to "2", except for "1". | Before: | Main Menu displayed |  | Functional
|  |  | After: 1. [Any value except "0" to "2"] | 1. An error message shall be displayed to remind the users only number "0" to "2" will be accepted | Boundary |  | Fail
|  |  | After (Nominal Value): 2. Your Choice? 1 | 2. The users shall see a empty 4x4 board with the message "Turn 1" shall be displayed to the users. The confiugration menu with an option rangning from "0" to "5" should be displayed to the users. A message "Build where?" is printed to prompt the user to enter a position |  |  | Pass
|  |  | After: 3. Values from "0" to "2" | 3. The system shall process the option value inputted accordingly |  |  | Pass

## US5 ok
Test Scenarios for SimpCity
| Test Cases Creation |  |  | System Testing (TDA) |  |  | User Acceptance Testing |  | Team
| User Stories: | US5 - As a user, I want to be able to input a number so that I can select the type of building to place down. |  | Version Control: | V1 |  | Version Control: | V1 | Scrum Master: | Megan Png
| Created By: | Hui Ying |  | Tester: |  |  | User: |  | Tech Lead: | Claris
| Dated as of: | 2021-12-15 |  | Test Date: |  |  | UAT Date: |  | QA: | Hui Ying
| Status: |  |  | Status: |  |  | Status:
| Reviwed By: |  |  | Reviwed By: |  |  | Reviwed By: |  | Developer: | Amanda Chan
| Tech Lead | <Signature> |  | Scrum Master | <Signature> |  | Scrum Master: | <Signature>
| Scrum Master | <Signature> |  |  |  |  | Tech Lead: | <Signature>
[7 empty] | QA: | <Signature>
| condition to test Start New Game Feautre | steps
S/NO | Test Scenario | Test Scenario Description | Test Values | Expected Outcome | Boundary? Equivalence? | Functional? Non-Functional? | Pass/ Fail | Actual Outcome | Test Result (Pass / Fail) | Remarks
1 | The number "1" is inputted by the user | 1. The user enters an option value of the numeric interger "1" when the message "Your Choice?" prompted | Before: Start New Game option is selected After: Your Choice? 1 | The message "Build where?" will be displayed to prompt the users to enter the location of the selected building to be placed | Equivalence | Functional | Pass
2 | The number "2" is inputted by the user | 1. The user enters an option value of the numeric interger "2" when the message "Your Choice?" prompted | Before: Start New Game option is selected After: Your Choice? 2 | The message "Build where?" will be displayed to prompt the users to enter the location of the selected building to be placed | Equivalence | Functional | Pass
3 | The number from "0" to "2" is not inputted by the user, then the user try again with the number "2", then with value from "3" to "5" or "0" | 1. The user enters an option value that is not a numeric interger of "0" to "2" when prompted 2. The user enters "0" to exit to the main menu 3. The user enters an option value of the numeric interger "2" when the message "Your Choice?" is prompted 4.The user enters "0" to exit to the main menu 5. The user enters any value from "3" to "5" 6. The user enters "0" to exit to the main menu 7. The users enter an option value that is not from "0" to "5" and is not a numeric interger | Before: | Start New Game option is selected |  | Functional |  |  |  |  | test failing is like for error message like you expect it to appear, out of bound, go the right position
|  |  | After: 1. Value from "0" to "2". | 1. The system shall process each option value from the menu as accordance. | Boundary |  | Pass
|  |  | After: 2. Nominal value: 2 | 2. The message "Build where?" shall be displayed to prompt the users to enter the location of the selected building to be placed |  |  | Pass
|  |  | After: 3. [Any value from "3" to "5"] | 3. The system shall not return any prompt or input. |  |  | Pass
|  |  | After: 4. [Any value expect "0" to "5" and not a numeric interger} | 4. The system shall display an error message shall be displayed to remind the users only number "0" to "5" will be accepted. |  |  | Fail

## US21TDD V3
Manual TDD Test Cases for US21
Scrum Master/ Project Manager | Megan Png |  | Signature
Tech Lead | Claris
QA | Hui Ying
Developer | Amanda Chan
Dated as of: | 2021-12-09
steps
S/NO | Created By | Test Scenario | Test Scenario Description | Test Values | Expected Outcome | Boundary? Equivalence? | Functional? Non-Functional? | Result Output | Pass/ Fail | Remarks
1 | Hui Ying | Can the main menu be printed when the program starts runnning? | 1. The developer runs the program to verify if the main menu is printed when the program start running | Before: Program is running After: Main menu printed out in the terminal | The function main_menu(main_menu_options) is called in the mainflow and the main menu is printed | Equivalence | Functional |  | Fail | The function main_menu(main_menu_options) is not called in the mainflow
2 | Hui Ying | Can the main menu be printed when the program starts runnning? | 1. The developer runs the program to verify if the main menu is printed when the program start running | Before: Program is running After: Main menu printed out in the terminal | The function main_menu(main_menu_options) is called in the mainflow with the input as a return | Equivalence | Functional |  | Pass | The function main_menu(main_menu_options) is called with a return of the variable choosen_menu_option
Manual Test Script

## US21TDD Version 1
Manual TDD Test Cases for US21
Scrum Master/ Project Manager | Megan Png |  | Signature |  |  | V2 | Corrected version
Tech Lead | Claris
QA | Hui Ying
Developer | Amanda Chan
Dated as of: | 20th November 2021
steps
S/NO | Created By | Test Scenario | Test Scenario Description | Test Values | Expected Outcome | Boundary? Equivalence? | Functional? Non-Functional? | Result Output | Pass/ Fail | Remarks
1 | Hui Ying | Can the main menu be printed when the program starts runnning? | 1. The developer runs the program to verify if the main menu is printed when the program start running | Before: Program is running After: Main menu printed out in the terminal | The function main_menu(main_menu_options) is called in the mainflow and the main menu is printed | Equivalence | Functional |  | Fail | The function main_menu(main_menu_options) is not called in the mainflow
2 | Hui Ying | Can the main menu be printed when the program starts runnning? | 1. The developer runs the program to verify if the main menu is printed when the program start running | Before: Program is running After: Main menu printed out in the terminal | The function main_menu(main_menu_options) is called in the mainflow with the input as a return | Equivalence | Functional | Functional | Pass | The function main_menu(main_menu_options) is called with a return of the variable choosen_menu_option
3 | Hui Ying | Can the user start a new game after the start new game option is selected? | 1. The developer runs the program to verify if option 1 in the main menu calls the configure_menu(configure_menu_options) | Before: Start new game option is selected After: The configure menu should be printed out. | The function configure_menu(configure_menu_options) is called after the option 1 is entered for the chosen_menu_options | Equivalence | Functional |  | Fail | The function is not called in the While true loop, hence reuslting only the message "Turn 1", and the option value "5. Save game", "0. Exit to main menu" and the choosen_configureMenu_option "Your Choice ?" is printed.
4 | Hui Ying | Can the user start a new game after the start new game option is selected? | 1. The developer runs the program to verify if option 1 in the main menu calls the configure_menu(configure_menu_options) | Before: Start new game option is selected After: The configure menu should be printed out. | The function configure_menu(configure_menu_options) is called after the option 1 is entered for the chosen_menu_options | Equivalence | Functional |  | Pass | The function is called in the While true loop, the configure menu is printed along with the message "Turn 1", the option value "5. Save game", "0.Exit to main menu" and the choosen_configureMenu_option that prints an input "Your Choice ?" is printed.
Manual Test Script

## US21 TDD V2
Manual TDD Test Cases for US21
Scrum Master/ Project Manager | Megan Png |  | Signature
Tech Lead | Claris
QA | Hui Ying
Developer | Amanda Chan
Dated as of: | 1st December 2021
steps
S/NO | Created By | Test Scenario | Test Scenario Description | Test Values | Expected Outcome | Boundary? Equivalence? | Functional? Non-Functional? | Result Output | Pass/ Fail | Remarks
1 | Hui Ying | Can the main menu be printed when the program starts runnning? | 1. The developer runs the program to verify if the main menu is printed when the program start running | Before: Program is running After: Main menu printed out in the terminal | The function main_menu(main_menu_options) is called in the mainflow and the main menu is printed | Equivalence | Functional |  | Fail | The function main_menu(main_menu_options) is not called in the mainflow
2 | Hui Ying | Can the main menu be printed when the program starts runnning? | 1. The developer runs the program to verify if the main menu is printed when the program start running | Before: Program is running After: Main menu printed out in the terminal | The function main_menu(main_menu_options) is called in the mainflow with the input as a return | Equivalence | Functional | Functional | Pass | The function main_menu(main_menu_options) is called with a return of the variable choosen_menu_option
3 | Hui Ying | Can the user start a new game after the start new game option is selected? | 1. The developer runs the program to verify if option 1 in the main menu calls the configure_menu(configure_menu_options) | Before: Start new game option is selected After: The configure menu should be printed out. | The function configure_menu(configure_menu_options) is called after the option 1 is entered for the chosen_menu_options | Equivalence | Functional |  | Fail | The function is not called in the While true loop, hence reuslting only the message "Turn 1", and the option value "5. Save game", "0. Exit to main menu" and the choosen_configureMenu_option "Your Choice ?" is printed.
4 | Hui Ying | Can the user start a new game after the start new game option is selected? | 1. The developer runs the program to verify if option 1 in the main menu calls the configure_menu(configure_menu_options) | Before: Start new game option is selected After: The configure menu should be printed out. | The function configure_menu(configure_menu_options) is called after the option 1 is entered for the chosen_menu_options | Equivalence | Functional |  |  | The function is called in the While true loop, the configure menu is printed along with the message "Turn 1", the option value "5. Save game", "0.Exit to main menu" and the choosen_configureMenu_option that prints an input "Your Choice ?" is printed.
Manual Test Script

## US5 Test Doc
Test Scenarios for Simp City - Start a New Game (System)
| Scrum Master/ Project Manager | Megan Png
| Tech Lead | Claris
| QA | Hui Ying
| Developer | Amanda Chan
|  | condition to test Start New Game Feautre | steps
S/NO | Created By | Test Scenario | Test Scenario Description | Test Values | Expected Outcome | Actual Outcome | Boundary? Equivalence? | Functional? Non-Functional? | Pass/ Fail | Remarks | Q: Do you want to verify they want to exit before they exit the main menu?
1 | Hui Ying | The user wants to start a new game | 1. The user enters an option value of the numeric interger "1" when prompted to start a new game | Before: Main Menu Displayed After: Enter Choice? 1 | The configuration menu and the 4x4 board is displayed to the user |  |  | Functional | Pass
2 | Hui Ying | The user wants to start a new game | 1. The user enters an option value of the numeric interger "1" when prompted to start a new game | Before: Main Menu Displayed After: Enter Choice? 1 | The configuration menu and the 4x4 board is not displayed to the user |  |  | Functional | Fail
3 | Hui Ying | The users want to start a new game | 1. The user wants to be able to enters an option value from the main menu option | Before: Python script needs to be run After: Main Menu displayed | Main menu is displayed to the users |  |  | Functional | Pass
4 | Hui Ying | The users want to start a new game | 1. The user wants to be able to enters an option value from the main menu option | Before: Python script needs to be run After: Main Menu is not displayed | Main menu is displayed to the users |  |  | Functional | Fail
5 | Hui Ying | The users want to start a new game | 1. The user enters an option value of the numeric interger "1" when prompted to start a new game | Before: Python script needs to be run After: Main Menu is not displayed | Main menu is displayed to the users |  | NIL | Functional | Pass

## US19
Test Scenarios for Simp City - US19 - As a user, I want to be able to see the computation of the final score so that I can understand how the points are calculated.
| Scrum Master/ Project Manager | Megan Png
| Tech Lead | Claris
| QA | Hui Ying
| Developer | Amanda Chan
|  | condition to test Start New Game Feautre | steps
S/NO | Created By | Test Scenario | Test Scenario Description | Test Values | Expected Outcome | Boundary? Equivalence? | Functional? Non-Functional? | Pass/ Fail | Remarks | Q: Do you want to verify they want to exit before they exit the main menu?
1 | Hui Ying | The number "0" is inputted by the user | 1. The user enters an option value of the numeric interger "0" when prompted | Before: Start New Game option is selected After: Your Choice? 0 | The user return to the main menu, the main menu options is display to them |  | Functional | Pass
2 | Hui Ying | The number "0" is inputted by the user | 1. The user enters an option value of the numeric interger "0" when prompted | Before: Start New Game option is selected After: Your Choice? 0 | The user did not return to the main menu, main menu options is not displayed to the users |  | Functional | Fail
3 | Hui Ying | The number"1" to "5" is inputted by the user | 1. The user enters an option value that is not a numeric interger of "0" but within the menu options when prompted | Before: Start New Game option is selected After: Your Choice? [Any input in the menu but not 0] | The options will be processed according to the menu options selected |  | Functional | Pass
4 | Hui Ying | The number"1" to "5" is inputted by the user | 1. The user enters an option value that is not a numeric interger of "0" but within the menu options when prompted | Before: Start New Game option is selected After: Your Choice? [Any input in the menu but not 0] | The users returns back to the main menu |  | Functional | Fail
5 | Hui Ying | The number""1" to "5" or "0" is not inputted by the user | 1. The user enters an option value that is not within the menu | Before: Start New Game option is selected After: Your Choice? [Anything not within the menu] | An error message will be displayed to remind the users that invalid input is captured | NIL | Functional | Pass
6 | Hui Ying | The number"1" to "5" or "0" is not inputted by the user | 1. The user enters an option value that is not within the menu | Before: Start New Game option is selected After: Your Choice? [Anything not within the menu] | An error message is not observed and the system is not reacting | NIL | Functional | Fail
7 | Hui Ying | The number"1" to "5" or "0" is not inputted by the user | 1. The user enters an option value that is not within the menu | Before: Start New Game option is selected After: Your Choice? [Anything not within the menu] | An error message is not observed and the options enter is processed accordingly | NIL | Functional | Fail

## Sheet1
3 | The number "3" is inputted by the user | 1. The user enters an option value of the numeric interger "3" when the message "Your Choice?" prompted | Before: Start New Game option is selected After: Your Choice? 3 | Remanining buildings available for the users to select is displayed to the users. | Equivalence | Functional | Pass
4 | The number "4" is inputted by the user | 1. The user enters an option value of the numeric interger "4" when the message "Your Choice?" prompted | Before: Start New Game option is selected After: Your Choice? 4 | The computation of score accmulated for each building and the current "Total Score: " is displayed to the users | Equivalence | Functional | Pass
5 | The number "5" is inputted by the user | 1. The user enters an option value of the numeric interger "5" when the message "Your Choice?" prompted | Before: Start New Game option is selected After: Your Choice? 5 | A verification message "Game saved" is displayed to indicate that the game was saved sucessfully | Equivalence | Functional | Fail
6 | The number "0" is inputted by the user | 1. The user enters an option value of the numeric interger "0" when the message "Your Choice?" is prompted | Before: Start New Game option is selected After: Your Choice? 0 | The user return to the main menu | Equivalence | Functional | Pass
7 | The number "0" to "5" is not inputted by the user | 1. The user enters an option value that is not a numeric interger of "0" to "5" when prompted | Before: Start New Game option is selected After: [Any value expect "0" to "5"" | An error message will be displayed to remind the users only number "0" to "5" will be accepted and the message "Build where?" will not be prompted. | Equivalence | Functional | Pass

## US9 ok
Test Scenarios for SimpCity
| Test Cases Creation |  |  | System Testing (TDA) |  |  | User Acceptance Testing |  | Team
| User Stories: | US9 - As a user, I want to be able to see my building that I have placed being displayed so that I have a visual representation of where my buildings are. |  | Version Control: | V1 |  | Version Control: | V1 | Scrum Master: | Megan Png
| Created By: | Hui Ying |  | Tester: |  |  | User: |  | Tech Lead: | Claris
| Status: | Done |  | Status: |  |  | Status: |  | QA: | Hui Ying
| Dated as of: | 2021-12-15 |  | Test Date: |  |  | UAT Date: |  | Developer: | Amanda Chan
| Reviwed By: |  |  | Reviwed By: |  |  | Reviwed By:
| Tech Lead | <Signature> |  | Scrum Master | <Signature> |  | Scrum Master: | <Signature>
|  |  |  | Tech Lead | <Signature> |  | Tech Lead: | <Signature>
[7 empty] | QA: | <Signature>
| condition to test place a building a the grid | steps
S/NO | Test Scenario | Test Scenario Description | Test Values | Expected Outcome | Boundary? Equivalence? | Functional? Non-Functional? | Pass/ Fail | Actual Outcome | Test Result (Pass / Fail) | Remarks
1 | The number "1" is inputted by the user in the configure menu to select the building to input, then enter the positon to place the building in the grid map. | 1. The user enters an option value of the numeric interger "1" when the message "Your Choice?" is prompted to the users, then the message "Build Where?" is prompted to the users and the user enters the desired position | Before: Start New Game option is selected. Empty 4x4 board with the message "Turn 1" shall be displayed. The confiugration menu with an option rangning from "0" to "5" should be displayed Build a building option is selected -> Your Choice? [option value 1 to 2] is enter After: Build where? [alphabet in Caps+ number, the alphabet should range from "A" to "D" and the number should range from "1" to "4". ] e.g C4 | The building name is displayed in the board with its position being the input indicated by the user when the message "Build Where" is prompted | Equivalence | Functional | Pass
2 | The number "2" is inputted by the user in the configure menu to select the building to input, then enter the positon to place the building in the grid map. | 1. The user enters an option value of the numeric interger "2" when the message "Your Choice?" is prompted to the users, then the message "Build Where?" is prompted to the users and the user enters the desired position | Before: Start New Game option is selected. Empty 4x4 board with the message "Turn 1" shall be displayed. The confiugration menu with an option rangning from "0" to "5" should be displayed Build a building option is selected -> Your Choice? [option value 1 to 2] is enter After: Build where? [alphabet in Caps+ number, the alphabet should range from "a" to "d" and the number should range from "1" to "4". ] e.g b2 | The building name is displayed in the board with its position being the input indicated by the user when the message "Build Where" is prompted | Equivalence | Functional | Pass
3 | The user selects the building to input in the configure menu, then enter the positon to place the building in the grid map. | 1. The user enters an option value of the numeric interger either "1" to "2" when the message "Your Choice?" is prompted to the users. 2. Then the message "Build Where?" is prompted to the users 3. The user enters a valur of [alphabet in Caps or lower case+ number, the alphabet should range from "a" to "d" or "A" to "D" and the number should range from "1" to "4". ] e.g. b2 4. The user enters [alphabet in Caps or lower case+ number, the alphabet should range beyond "a" to "d" or "A" to "D" and the number is beyond "1" to "4". ] e.g. Z1 5. The user restart the program again 6. The user starts a new game and enters an option value of the numeric interger either "1" to "2" when the message "Your Choice?" is prompted to the users. 7. Then the message "Build Where?" is prompted to the users. 8. The user enters [A combintation of not a alphabet + number is entered] e.g. 55 | Before: | Before: Start New Game option is selected. Empty 4x4 board with the message "Turn 1" shall be displayed. The confiugration menu with an option rangning from "0" to "5" should be displayed Build a building option is selected -> Your Choice? [option value 1 to 2] is enter |  | Functional
|  |  | After: 1.Build where? [alphabet in Caps or lower case+ number, the alphabet should range from "a" to "d" or "A" to "D" and the number should range from "1" to "4". ] | 1. The building name is displayed in the board with its position being the input indicated by the user when the message "Build Where" is prompted | Boundary |  | Pass
|  |  | After: 2. Build where? [alphabet in Caps or lower case+ number, the alphabet should range beyond "a" to "d" or "A" to "D" and the number is beyond "1" to "4". ] | Error in program as input validation was not done yet. |  |  | Fail
|  |  | After: 3. Build where? [A combintation of not a alphabet + number is entered] | Error in program as input validation was not done yet. |  |  | Fail

## US6 Sprint 3
Test Scenarios for SimpCity
| Test Cases Creation |  |  | System Testing (TDA) |  |  | User Acceptance Testing |  | Team
| User Stories: | US6 - As a user, I want to be able to see my building that I have placed being displayed so that I have a visual representation of where my buildings are. |  | Version Control: | V1 |  | Version Control: | V1 | Scrum Master: | Megan Png
| Created By: | Hui Ying |  | Tester: |  |  | User: |  | Tech Lead: | Claris
| Status: | Done |  | Status: |  |  | Status: |  | QA: | Hui Ying
| Dated as of: | 2021-01-04 |  | Test Date: |  |  | UAT Date: |  | Developer: | Amanda Chan
| Reviwed By: |  |  | Reviwed By: |  |  | Reviwed By:
| Tech Lead | <Signature> |  | Scrum Master | <Signature> |  | Scrum Master: | <Signature>
|  |  |  | Tech Lead | <Signature> |  | Tech Lead: | <Signature>
[7 empty] | QA: | <Signature>
| condition to test place a building a the grid | steps
S/NO | Test Scenario | Test Scenario Description | Test Values | Expected Outcome | Boundary? Equivalence? | Functional? Non-Functional? | Pass/ Fail | Actual Outcome | Test Result (Pass / Fail) | Remarks
1 | A combination of lower letter case alphabet and a number is inputted by the users. The alphbert entered by the user is not between "a" to "d" or the number entered is not ranging between "1" to "4". | Before: The users is in a game and build a building option is selected from the configuration menu, e.g. [Build a HSE] --> Build Where? |  |  | Boundary | Functional | Fail
|  | 1. The user selects the option of either "1" or "2" in the configuration menu to build a building 2.The user enters the location with a combination of lower letter case alphabet and a number. The letter is not between "a" to "d" or the number is not ranging between "1" to "4" . E.g. [a9] or [z1] | 1. The user enters the location with a combination of lower letter case alphabet and a number. The letter is not between "a" to "d" or the number is not ranging between "1" to "4" . E.g. [a9] or [z1] After: Building name did not appear in the position inputted | An error message is displayed to remind the user to input the correction positioning location
2 | A combination of lower letter case alphabet and a number ranging between "a" to "d" and a number ranging between "1" to "4" is inputted by the user | 3. The user enters the location with a combination of lower letter case alphabet ranging between "a" to "d" with a number ranging between "1" to "4". E.g. [a4] | 1. The user enters the location with a combination of lower letter case alphabet ranging between "a" to "d" and a number ranging between "1" to "4". E.g. [a4] After: Building name appear in the position inputted of the 4x4 board | The user sees the building name displayed in the grid of the position they indicated |  |  | Pass
3 | A combination of Upper letter case alphabet and a number is inputted by the users. The alphbert entered by the user is not between "A" to "D" or the number entered is not ranging between "1" to "4". | 1. The user selects the option of either "1" or "2" in the configuration menu to build a building 2.The user enters the location with a combination of upper letter case alphabet and a number. The letter is not between "A" to "D" or the number is not ranging between "1" to "4" . E.g. [A9] or [Z1] | 1. The user enters the location with a combination of upper letter case alphabet and a number. The letter is not between "A" to "D" or the number is not ranging between "1" to "4" . E.g. [A9] or [Z1] After: Building name appear in the position inputted | An error message is displayed to remind the user to input the correction positioning location |  |  | Fail
4 | A combination of upper letter case alphabet amd a number is inputted by the user. The alperbert enterd ranges between "A" to "D" and a number rangwa between "1" to "4" | 3. The user enters the location with a combination of lower letter case alphabet ranging between"A" to "D" with a number ranging between "1" to "4". E.g. [A4] | 1. The user enters the location with a combination of lower letter case alphabet ranging between"A" to "D" with a number ranging between "1" to "4". E.g. [A4] After: Building name appear in the position inputted | The user sees the building name displayed in the grid of the position they indicated |  |  | Pass
5 | A combination of upper or lower letter case alphabet amd a number is inputted by the user. The alperbert enterd does not ranges between "A" to "D" or "a" to "d" and a number does not ranges between "1" to "4" is inputted | 3. The user enters the location with a combination of lower or upper letter case alphabet and a number. The alperbert enterd does not ranges between"A" to "D" or "a" to "d" with a number that does not ranges between "1" to "4". E.g. [z7] or [S7] | 1. The alperbert enterd does not ranges between"A" to "D" or "a" to "d" with a number that does not ranges between "1" to "4".E.g. [z7] or [S7] After: Error message appear. | An error message is displayed to remind the user to input the correction positioning location | Equivalence | Functional | Fail

## US7 Sprint 3
Test Scenarios for SimpCity
| Test Cases Creation |  |  | System Testing (TDA) |  |  | User Acceptance Testing |  | Team
| User Stories: | US7 - As a user, I want to be given a prompt to verify my decision in choosing a type of building so I do not accidentally choose the type that I do not want. |  | Version Control: | V1 |  | Version Control: | V1 | Scrum Master: | Megan Png
| Created By: | Hui Ying |  | Tester: |  |  | User: |  | Tech Lead: | Claris
| Status: | Done |  | Status: |  |  | Status: |  | QA: | Hui Ying
| Dated as of: | 2021-01-05 |  | Test Date: |  |  | UAT Date: |  | Developer: | Amanda Chan
| Reviwed By: |  |  | Reviwed By: |  |  | Reviwed By:
| Tech Lead | <Signature> |  | Scrum Master | <Signature> |  | Scrum Master: | <Signature>
|  |  |  | Tech Lead | <Signature> |  | Tech Lead: | <Signature>
[7 empty] | QA: | <Signature>
| condition to test place a building a the grid | steps
S/NO | Test Scenario | Test Scenario Description | Test Values | Expected Outcome | Boundary? Equivalence? | Functional? Non-Functional? | Pass/ Fail | Actual Outcome | Test Result (Pass / Fail) | Remarks
1 | The user selects the build a building option and selects enter. A message will be prompted to the users to verify the type of building choosen so that the user would not accidentally choose the building he or she do not want. | 1. The users selects a the Start a new game or Load saved game option in the main menu. 2. The user selects option 1 or option 2 in the confiugration menu, e.g. [1. Build a HSE] [2. Build a BCH] | Before: The users is in a game and build a building option is selected from the configuration menu, e.g. [Build a HSE] --> Build Where? After: A confirmation message will be prompted to the users. | A confirmation message is be prompted to the users to prompt the user to verfiy their decesion made in choose the type of building to be placed in the 4x4 grid. | Equivalence | Functional | Pass
2
3
4
5
6
7

## US8 Sprint 3
Test Scenarios for SimpCity
| Test Cases Creation |  |  | System Testing (TDA) |  |  | User Acceptance Testing |  | Team
| User Stories: | US10 - As a user, I would like to be able to see a notification to notify me of invalid moves so that I do not select an invalid area to place my building |  | Version Control: | V1 |  | Version Control: | V1 | Scrum Master: | Megan Png
| Created By: | Hui Ying |  | Tester: |  |  | User: |  | Tech Lead: | Claris
| Status: | Done |  | Status: |  |  | Status: |  | QA: | Hui Ying
| Dated as of: | 2021-01-06 |  | Test Date: |  |  | UAT Date: |  | Developer: | Amanda Chan
| Reviwed By: |  |  | Reviwed By: |  |  | Reviwed By:
| Tech Lead | <Signature> |  | Scrum Master | <Signature> |  | Scrum Master: | <Signature>
|  |  |  | Tech Lead | <Signature> |  | Tech Lead: | <Signature>
[7 empty] | QA: | <Signature>
| condition to test place a building a the grid | steps
S/NO | Test Scenario | Test Scenario Description | Test Values | Expected Outcome | Boundary? Equivalence? | Functional? Non-Functional? | Pass/ Fail | Actual Outcome | Test Result (Pass / Fail) | Remarks
1 | The user selects the build a building option and selects enter and confirm the decesion on the building type. The message "Build Where?" is prompted, the user will enter his or her desired location and a confirmation message will be prompted to verfiy the position the user have entered. | 1. The users selects a the Start a new game or Load saved game option in the main menu. 2. The user selects option 1 or option 2 in the confiugration menu, e.g. [1. Build a HSE] [2. Build a BCH] 3. The user confirm his or her decsion on the building type. 4. The message "Build Where?" is prompted 5. The user enters a location e.g [B4] 6. A message should bbe prompted to the users to verfiy the location that the user have entered. | Before: The users is in a game and build a building option is selected from the configuration menu, e.g. [Build a HSE] --> Build Where? 1. The user enters the location with a combination of lower letter case alphabet ranging between "a" to "d" with a number ranging between "1" to "4". E.g. [a4] After: A confirmation message will be prompted to the users. | A confirmation messagel be prompted to the users to prompt the user to verfiy the location the user have entered to be placed in the 4x4 grid. | Equivalence | Functional | Pass
2

## US12 Sprint 3
Test Scenarios for SimpCity
| Test Cases Creation |  |  | System Testing (TDA) |  |  | User Acceptance Testing |  | Team
| User Stories: | US12 - As a user, I would like to input letter-number pairs in either upper or lowercase so that I do not have to switch to a specific type of lettering casing when I am playing the game. |  | Version Control: | V1 |  | Version Control: | V1 | Scrum Master: | Megan Png
| Created By: | Hui Ying |  | Tester: |  |  | User: |  | Tech Lead: | Claris
| Status: | Done |  | Status: |  |  | Status: |  | QA: | Hui Ying
| Dated as of: | 2021-01-06 |  | Test Date: |  |  | UAT Date: |  | Developer: | Amanda Chan
| Reviwed By: |  |  | Reviwed By: |  |  | Reviwed By:
| Tech Lead | <Signature> |  | Scrum Master | <Signature> |  | Scrum Master: | <Signature>
|  |  |  | Tech Lead | <Signature> |  | Tech Lead: | <Signature>
[7 empty] | QA: | <Signature>
| condition to test place a building a the grid | steps
S/NO | Test Scenario | Test Scenario Description | Test Values | Expected Outcome | Boundary? Equivalence? | Functional? Non-Functional? | Pass/ Fail | Actual Outcome | Test Result (Pass / Fail) | Remarks
1 | The user selects the build a building option and selects enter and confirm the decesion on the building type. The message "Build Where?" is prompted, the user enters a desired location using upper case letter for its alphabert and number combination for indication of location. | 1. The users selects a the Start a new game or Load saved game option in the main menu. 2. The user selects option 1 or option 2 in the confiugration menu, e.g. [1. Build a HSE] [2. Build a BCH] 3. The user confirm his or her decsion on the building type. 4. The message "Build Where?" is prompted 5. The user enters a location e.g [B4] 6. The systemshould accpects the input and a message should bbe prompted to the users to verfiy the location that the user have entered. | Before: The users is in a game and build a building option is selected from the configuration menu, e.g. [Build a HSE] --> Build Where? 1. The user enters the location with a combination of lower letter case alphabet ranging between "A" to "D" with a number ranging between "1" to "4". E.g. [B4] After: A confirmation message will be prompted to the users. | The system accpects the input as a confirmation messagel be prompted to the users to prompt the user to verfiy the location the user have entered to be placed in the 4x4 grid. | Equivalence | Functional | Pass
2 | The user selects the build a building option and selects enter and confirm the decesion on the building type. The message "Build Where?" is prompted, the user enters a desired location using lower case letter for its alphabert and number combination for indication of location. | 7. The user verifies the location entered. 8. The congifuration menu is being prompted, the user selects option 1 or option 2 in the confiugration menu, e.g. [1. Build a HSE] [2. Build a BCH]. 9. The user confirm his or her decsion on the building type. 10. The message "Build Where?" is prompted 11. The user enters a location e.g [b4] 12. The system should accpects the input and a message should bbe prompted to the users to verfiy the location that the user have entered. | Before: The users is in a game and build a building option is selected from the configuration menu, e.g. [Build a HSE] --> Build Where? 1. The user enters the location with a combination of lower letter case alphabet ranging between "a" to "d" with a number ranging between "1" to "4". E.g. [b4] After: A confirmation message will be prompted to the users. | The system accpects the input as a confirmation messagel be prompted to the users to prompt the user to verfiy the location the user have entered to be placed in the 4x4 grid. | Equivalence | Functional | Pass
2
3
4
5
6
7

## US17 Sprint 3
Test Scenarios for SimpCity
| Test Cases Creation |  |  | System Testing (TDA) |  |  | User Acceptance Testing |  | Team
| User Stories: | US17 - As a user, I want to be able to leave the main menu at any point during the 16 rounds. |  | Version Control: | V1 |  | Version Control: | V1 | Scrum Master: | Megan Png
| Created By: | Hui Ying |  | Tester: |  |  | User: |  | Tech Lead: | Claris
| Status: | Done |  | Status: |  |  | Status: |  | QA: | Hui Ying
| Dated as of: | 2021-01-06 |  | Test Date: |  |  | UAT Date: |  | Developer: | Amanda Chan
| Reviwed By: |  |  | Reviwed By: |  |  | Reviwed By:
| Tech Lead | <Signature> |  | Scrum Master | <Signature> |  | Scrum Master: | <Signature>
|  |  |  | Tech Lead | <Signature> |  | Tech Lead: | <Signature>
[7 empty] | QA: | <Signature>
| condition to test place a building a the grid | steps
S/NO | Test Scenario | Test Scenario Description | Test Values | Expected Outcome | Boundary? Equivalence? | Functional? Non-Functional? | Pass/ Fail | Actual Outcome | Test Result (Pass / Fail) | Remarks
1 | The user is currently in a game and wants to exit the game, hence the option "0" is selected from the configurayion to exit to the main meu | 1. The users selects a the Start a new game or Load saved game option in the main menu. 2. The users starts to play the game by building a new building or check remaining buildings or check current score. 3. The user selects the number "0" from the configuration menu when the message "Your Choice" is prompted. 4. The user enters the option number "0" to exit to the main menuu | Before: The users is in a game --> Your Choice? 1. The user enters the integer "0" when the message "Your Choice is prompted. After: Your Choice? 0 | The user return back to the main menu | Boundary | Functional | Pass
2 | The user is currently in a game and wants to exit the game, the user enters the option that is not a numeric integer. | 1. The users selects a the Start a new game or Load saved game option in the main menu. 2. The users starts to play the game by building a new building or check remaining buildings or check current score. 3. The user enters a value that is not a numeric integer when the message "Your Choice" is prompted. | Before: The users is in a game --> Your Choice? 1. The user a value that is not a numeric interger when the message "Your Choice is prompted. After: Your Choice? a | The user did not return back to the main menu and an error message will appear to remind the user an invalid option is selected | Boundary | Functional | Fail
2 | The user is currently in a game and wants to exit the game, the user enters the option that is not the numeric integer "0", bur ranges between "1" to "5" | 1. The users selects a the Start a new game or Load saved game option in the main menu. 2. The users starts to play the game by building a new building or check remaining buildings or check current score. 3. The user enters a value that is not a numeric integer but ranges between "1" to "5" when the message "Your Choice" is prompted. | Before: The users is in a game --> Your Choice? 1. The user a value that ragnes between the number integer "1" to "5" when the message "Your Choice is prompted. After: Your Choice? 3 | The user will not return back to the main menu, instead the user will be viewing the remaining buildings left in the game. | Boundary | Functional | Pass